## Slide 1: Subteam Intros
Notes: Intros to officers. OFFICERS ARRIVE 15 MINS EARLY

## Slide 2: Subteam workflow
Each team will have one of the following:
  Communications focal
    Determine how your group will communicate with each other
  Participation focal
    Track attendance, make sure members are contributing
  Documentation focal
    Responsible for meeting notes, documenting challenges and accomplishments
  Product focal
    Responsible for reporting progress to your lead
  Engagement focal
    Responsible for getting info from other subteams

## Slide 3: Set up a communication method
Discord group chat? A channel in the server? iMessage? Microsoft Teams? There are many ways to communicate with your group. Pick one and stick to it.

## Slide 4: Establish a working plan
What is your communication method? Will you meet outside of our club meetings? If so, when and how often? What happens if someone is sick and misses a meeting? What are your participation expectations? How will changes to the plan be approved?
Deliverable: submit a pull request to main with a commit of a Markdown (.md) file with your working plan to the ML Classifier /doc repository

## Slide 5: Subteams

## Slide 6: Today’s Agenda
Get into Subteams
Make a working plan together
First task: commit your plan to the GitHub repository!
Notes: Josh talk about Bot if finished?

## Slide 7: Sensors
Responsibilities
1. Select and procure input components (camera, microphone, buttons, etc.)
2. Interface sensors with the platform board (via I²C, SPI, USB, etc.)
3. Validate sensor performance (resolution, framerate, latency, noise)
4. Provide clear APIs or data streams for the Control team
Deliverables
• Hardware schematic or wiring diagram
• Driver scripts or libraries
• Data quality report (FPS, resolution consistency)
• “Input API” spec: how other teams request data
Tools
• Physical sensor LRUs (Line Replaceable Units)
• OpenCV, ffmpeg
• Oscilloscope / logic analyzer
• Python or C++ for interface testing
Purpose
Design, assemble, and validate all hardware and software components that provide inputs to the system.

## Slide 8: Actuation
Responsibilities
1. Choose output devices (display, LEDs, speakers, servos, etc.)
2. Develop control logic for each device (brightness, tone, movement, etc.)
3. Define the output protocol for Control team integration
4. Test timing, latency, and reliability of output actuation
Deliverables
• Wiring diagrams
• Output control library or function calls
• Response timing log
• Output API documentation
Tools
• GPIO libraries, PWM drivers
• Soldering equipment
• Oscilloscope, multimeter
• Optional: PyGame or Kivy for GUI display
Purpose
Develop and control all user-facing feedback and physical actions that occur as a result of facial recognition.

## Slide 9: Platform Formerly Firmware
Responsibilities
1. Select and bring up the development board (e.g., Pi, Jetson)
2. Configure OS, drivers, libraries, and storage
3. Ensure interfaces (USB, I²C, GPIO, SPI) are functional
4. Manage power, cooling, and reliability
5. Support Control and Input/Output teams with infrastructure
Deliverables
• Platform configuration guide
• Hardware setup checklist
• Performance validation report
• Interface availability matrix
Tools
• Balena Etcher
• VS Code Remote SSH
• Linux tools (htop, vcgencmd, iostat)
Purpose
Develop the embedded computing platform, install the OS, manage drivers, and ensure reliable hardware operation

## Slide 10: Control Formerly Computing
Responsibilities
1. Manage real-time data acquisition from sensors (create a dummy pipeline)
2. Run inference using the ML model (e.g., TensorFlow Lite)
3. Implement control flow logic and state machines
4. Send commands to Output team’s devices
5. Test and optimize system latency and reliability with Systems team
Deliverables
• main.py or main.cpp orchestrator
• Integration test script
• Control flow/state diagram
• Latency and performance report
Tools
• Python/C++
• JetPack / TensorFlow Lite / ONNX Runtime / OpenVINO
• OpenCV, NumPy
Purpose
Implement the main control and logic software that connects Input → ML → Output, using the Software team’s trained model.

## Slide 11: Systems Formerly Requirements
Responsibilities
1. Requirements Definition: Write measurable, verifiable requirements for each subteam.
2. System Architecture: Create a Simulink model showing how information moves from sensors → ML → actuation. Define interfaces between subteams (signal type, data rate, voltage, etc.).
3. Validation & Verification Planning: Develop a verification matrix that lists how each requirement will be tested (e.g., bench test, simulation, field test). Oversee end-to-end integration testing.
Deliverables
• System Simulink model (.slx)
• State machine diagram (e.g., “Device Stateflow model”)
• Verification plan spreadsheet
Tools
• MATLAB/Simulink + Stateflow for models
• Mermaid for visual diagrams
• Excel/Google Sheets (.csv) for requirements traceability
⸻
⚖️ How All Teams Interlock (End-to-End Data Path)
Systems
↓
+----------------+
| Platform | ← provides OS, power, ports, and drivers
+----------------+
↓
+-------+ +--------+
| Input | --> | Control| --> [ML model → decision logic]
+-------+ +--------+
↓
+--------+
| Output |
+--------+
⸻
🚀 How to Launch the Project (Next 2–4 Weeks)
Week Team Focus Deliverables
1 Systems defines baseline requirements & builds initial Simulink system model Req doc, block diagram
2 Platform brings up hardware; Input gets camera working Camera feed verified
3 Control integrates dummy recognition (e.g., color detection); Output reacts End-to-end “fake” demo
4 Replace dummy model with real ML; Systems validates timing vs. spec Full working prototype
⸻
Would you like me to create a Simulink-style block diagram (or visual schematic) showing how the five teams’ responsibilities connect and what data flows between them? It’ll help the Systems team understand what to model and simulate.
Purpose
Translate the high-level project idea into engineerable requirements, maintain system-level understanding, and validate that the integrated device meets the technical intent.

## Slide 12: Thanks for coming!

## Slide 13: Sam Timeline Notes (Not for Presenting)
⚙️ Assumptions
• Timeline: 12 weeks (one semester or term)
• Workload: ~2–3 hrs per member per week
• Team structure: 5 subteams
• Goal: Deliver a functional demo system (facial recognition → hardware response)
• Parallel effort: All teams work concurrently, but align through weekly syncs
⸻
🧭 12-Week Concurrent Itinerary
Each week below lists:
• 🎯 Theme / Milestone
• 🧩 Tasks per Subteam
• 💡 Learning Focus
⸻
🗓 Week 1 — Kickoff & Orientation
🎯 Establish team structure, goals, and tools.
Team Tasks Learning Focus
Systems Facilitate kickoff, finalize project scope, draft high-level requirements What is a requirement? What makes one testable?
Input Research camera modules, learn how image capture works Basics of digital imaging, camera interfaces
Output Brainstorm feedback options (LEDs, screen, sound), learn GPIO Intro to GPIO and actuators
Platform Unbox boards, verify boot (e.g., Raspberry Pi OS) Linux basics, SSH, file systems
Control Install Python, OpenCV, TensorFlow Lite Environment setup, simple I/O programming
⸻
🗓 Week 2 — Tool Setup & Initial Prototypes
🎯 Get everyone’s tools and environments functional.
Team Tasks Learning Focus
Systems Create draft system block diagram; choose Simulink or draw.io System thinking & signal flow
Input Capture live camera feed to laptop; test OpenCV VideoCapture() Image acquisition
Output Blink an LED or play a tone from the dev board GPIO programming
Platform Configure Wi-Fi, SSH, update OS, install libraries Linux package management
Control Write test script that prints “System Ready” Basic scripting, Git usage
⸻
🗓 Week 3 — Subsystem Foundations
🎯 Each team demonstrates basic standalone functionality.
Team Tasks Learning Focus
Systems Develop initial Simulink block diagram or timing model Simulink modeling
Input Stream camera to board, capture and display frames Data handling, latency
Output Control multiple GPIO devices; test timing PWM, hardware timing
Platform Verify all ports (USB, GPIO, I²C) function Hardware I/O
Control Simulate data pipeline (dummy input → dummy output) Software architecture
⸻
🗓 Week 4 — Interface Planning
🎯 Define how subsystems communicate.
Team Tasks Learning Focus
Systems Write interface control document (ICD): signal names, units, data rate Systems engineering documents
Input Define camera data output format (e.g., raw image, resized array) Data formatting
Output Define accepted commands (“display X,” “light Y”) Communication protocols
Platform Test simple data exchange (serial/I²C) Data buses
Control Build message-passing prototype (e.g., “if X then LED on”) Software integration
⸻
🗓 Week 5 — Learning & Dummy Integration
🎯 Connect first “mock” end-to-end system.
Team Tasks Learning Focus
Systems Simulate end-to-end timing in Simulink Timing validation
Input Feed a static image to Control team Frame buffering
Output Respond to dummy commands from Control Event handling
Platform Optimize board setup, verify temperature/power System maintenance
Control Combine input stream + dummy logic + output Software flow control
🎬 Demo goal: A light turns on when a face-shaped image appears (no ML yet).
⸻
🗓 Week 6 — ML & Data Introduction
🎯 Begin working with a pretrained face detection model.
Team Tasks Learning Focus
Systems Update requirements based on early results Requirements iteration
Input Capture and store multiple sample frames Data collection
Output Develop improved feedback (audio, screen) UX design
Platform Install TensorFlow Lite or PyTorch Mobile Library setup
Control Run a sample face detector model (OpenCV or TFLite) ML inference basics
🎬 Demo goal: Show real-time face detection with bounding box or LED signal.
⸻
🗓 Week 7 — Team Integration
🎯 All subteams connect through defined interfaces.
Team Tasks Learning Focus
Systems Verify interfaces in Simulink or flow diagram Interface verification
Input Stream live data to Control Data pipeline reliability
Output Sync outputs with Control signals Response synchronization
Platform Monitor CPU usage & optimize performance Profiling
Control Integrate Input + ML + Output Event-driven programming
🎬 Demo goal: Real camera → live detection → LED or display reaction.
⸻
🗓 Week 8 — Refinement & Error Handling
🎯 Improve robustness and speed.
Team Tasks Learning Focus
Systems Create test plan and validation checklist Test planning
Input Handle bad frames / low light Signal integrity
Output Add multiple response modes State-driven actuation
Platform Automate boot/startup scripts Bash scripting
Control Implement state machine (Idle / Detect / Recognized / Error) State logic design
⸻
🗓 Week 9 — Model Customization & Tuning
🎯 Connect to Software team’s trained facial recognition model.
Team Tasks Learning Focus
Systems Update Simulink with timing data from test runs Modeling latency
Input Provide sample images for model testing Dataset contribution
Output Refine feedback design UX iteration
Platform Ensure storage and model files fit File management
Control Swap dummy model for real one; verify inference Integration testing
🎬 Demo goal: Recognize known faces; trigger custom output.
⸻
🗓 Week 10 — Validation
🎯 Test requirements end-to-end.
Team Tasks Learning Focus
Systems Execute verification plan Testing methodology
Input Measure input latency Data timing
Output Measure actuation delay Output calibration
Platform Record thermal and CPU data Performance testing
Control Log recognition accuracy Debugging, optimization
⸻
🗓 Week 11 — Integration Freeze & Polish
🎯 System integration complete; focus on reliability and presentation.
Team Tasks Learning Focus
Systems Document final system behavior Reporting
Input Ensure stable data stream Reliability testing
Output Design final UI/UX Communication
Platform Package system, reduce boot time Deployment
Control Add error recovery and logging Defensive coding
⸻
🗓 Week 12 — Demo & Reflection
🎯 Present the system and reflect on engineering process.
Team Tasks Learning Focus
Systems Lead final verification review; show Simulink vs real results Model-based validation
Input Present camera subsystem results Communication of results
Output Present feedback behavior Demo delivery
Platform Present platform performance report Reliability
Control Run final demo live System orchestration
🎬 Final Demo Goal:
The system identifies an enrolled user in real time and provides personalized visual/audio feedback on a self-contained embedded platform.
⸻
🧠 Pedagogical Design (Why This Works)
• Parallel Progress: Every team has visible weekly progress, reducing idle time.
• Learning First: Each week alternates between learning skill → applying it.
• Early Integration: A working prototype appears around Week 5–6, motivating everyone.
• System Thinking: Systems team models while others build; everyone sees the “big picture.”
⸻
Would you like me to make a visual semester roadmap (Gantt-style timeline or swimlane chart)** showing all five teams’ work week-by-week?** It’s great for presenting to the club and tracking progress visually.